City of Derby - Board of Education

Field House and Baseball Field Building Committee

____________________________________________________________________________________

October 25, 2018

Derby Middle School Cafetorium

73 Chatfield St.

Present Field House and Baseball Field Building Committee Board Members:

Dr. Matthew Conway

Mr. Anthony DeFala

Mr. Dan Foley

Mr. George Kurtyka

Mrs. Laura Harris

Mrs. Janine Netto

Mr. Jim Gildea

Mrs. Debra Borrelli

Mr. Edward Armeno

Absent Field House and Baseball Field Building Committee Board Members:

Mr. Kenneth Marcucio

Mr. Andrew Cota

Mr. Ted Estwan

Mr. Martin Pascale

Mr. George French

Mr. Peter Olenoski

Mrs. Casey Picheco

Mrs. Rebecca O’Hara

Mr. Charles Sampson

Call to Order

Pledge of Allegiance

Roll Call   Taken at 6:25 p.m.

Public Portion

No one from the public wished to speak

Motion Passed:  That the public portion is closed by Anthony DeFala and second by George Kurtyka.  Motion carried unanimously.

Approval of minutes

Motion Passed:  That the Field House and Baseball field Building Committee minutes for October 2, 2018 be approved, as written by George Kurtyka and second by Anthony DeFala.  Motion carried unanimously.

Update from the Project Manager.

No one was present.

Approval of invoices:

Motion Passed:  That the Field House and Baseball field Building Committee approve invoice dated 10/10/18 for September services from JLL in the amount of $17,700.00 with the portion charged for mileage denied, by Anthony DeFala and second by Ed Armeno.  Motion carried unanimously.

Discussion on the motion.  Mr. Izzo explained that the monthly payment is $17,700 and this is their second to last payment.  They added on $1,951.21 for mileage that has been denied.  This charge is not part of their contract.

Motion Passed:  That the Field House and Baseball field Building Committee approve invoice for application #5 in the amount of $600,993.33 from Turner Construction for services through September 30, 2018 as recommended by Mr. Izzo, by Laura Harris and second by Edward Armeno.  Motion carried unanimously.

Correspondence

Dr Conway continues to apprise Ms. Payden on the Committee’s progress.  The foundation is being backfilled.  Blasting is done.  Steel should begin the first week of November.  Work is beginning on the retaining wall.  Finish dates have moved up with the field originally slated for 6/15/2019 now scheduled for April 15, 2019 for the start of the baseball season and the field house originally slated for 8/15/2019 now scheduled for June 15, 2019.  The desired goal is to have Ms. Payden at the graduation ceremonies as guest speaker presenting from the new field house balcony.

Dr. Conway noted through value engineering the contractors have been able to make cost saving alterations to the prefab wall materials as well as other measures that will keep control of the budget.

Mr. Foley asked if there could be publication of the projected dates of completion.  Dr. Conway noted that the projected dates are dependent on favorable weather conditions but most certainly as the schedule seems to be coming into focus, it would be appropriate for press releases on the progress.

Executive Session:

No session was needed.

Adjourn

Motion Passed:  That the Field House and Baseball field Building Committee adjourn at 6:35 p.m. Motion by George Kurtyka and second by Anthony DeFala.  Motion carried unanimously.

Respectfully submitted;

Karen M. Kemmesies

Karen M. Kemmesies

These minutes are subject to the Commission’s approval at their next scheduled meeting.